## INTRO
Planning Level Cost Estimating Tool For Bicycle Infrastructure Projects
This planning level cost estimating tool has been developed by the Maryland Department of Transportation and the Baltimore Regional Transportation Board's Bicycle and Pedestrian Advisory Group. The purpose of this estimator is to provide guidance to local jurisdictions on project design and construction costs associated with bicycle infrastructure. Cost estimates within this tool are developed by identifying pay items and establishing generalized quantities. This tool aims to cover a wide range of possible expenses that are typically incurred with bicycle projects, but cannot account for all possible items. To account for increased costs as design progresses, a 30% continency is included to allow for items not yet designed. The cost estimator is also provided as a general planning tool to compare costs from planning, develpoment and engineering professionals.
The cost estimating tool is based on American Association of State Highway Transportation Officials (AASHTO) and Maryland Manual of Uniformed Traffic Control Devices (MDMUTCD) standards for facility design, pavement markings, sign placement and other standards. The standards are incorporated into quantity calculations based on the project length and other user preferences.
The cost estimating tool is incorporates quantity formulas based on the project specifics. Users only need to input data into the orange fieds (project length, the number of intersections and average intersction width) to calcuate the remaining costs.
As no two bicycle facilities are exactly alike, this tool is divided into bicycle facility types to allow for more accurate estimates. Each facility type is located on separate tabs. The below TABLE OF CONTENTS list varying bicycle facilities and descriptions to help identify the appropriate facility to use.
Note that this estimator includes generalized costs for asphalt, concrete, grading, drainage improvements, limited utility relocation, pavement markings, signs and traffic signal adjustments. The estimate does not include construction management, special site remediation or the cost for ongoing maintenance. A cost range has been assigned to some general categories; however, these costs can vary widely depending on the exact details and nature of the work. The overall estimates are intended to be general and used for planning purposes. Construction costs will vary based on the ultimate project scope, implementation schedule, and economic conditions at the time of construction.
Additional Costs Associated with Construction Projects
In addition to design and construction costs, various costs are associated with capital project preparation. These costs include preparing environmental documentation, performing a hydrologic and hydraulic study and establishing easements or acquiring properties, identifying historic or cultural resources, endangered species or contaminated site remediation.
For shared-use path projects that include lighting, coordination for the installation, maintenance, operation and expenditure needs to be coordinated among stakeholders. Metering and billing are critical items which need to be determined prior to the lighting design.
Planning level cost estimates aim to cover a wide range of possible expenses that are typically incurred with projects, but cannot account for all possible items. The cost estimator is also provided as a general planning tool to compare costs from planning, development and engineering professionals.

## Table of Contents
Planning Level Cost Estimating Tool For Bicycle Infrastructure Projects
Table of Contents
Bicycle Facility Type | Tab | Description
Shared Lane | Shared Lane | A shared lane is represented by conditions where bicycle traffic shares a travel lane with motor vehicle traffic. While a shared lane is not a dedicated bicycle facility, the tab accounts for shared lane markings, also known as sharrows, and related signage for one travel direction.
Shared Lane | Shared Lanes | A shared lane is represented by conditions where bicycle traffic shares a travel lane with motor vehicle traffic. While a shared lane is not a dedicated bicycle facility, the tab accounts for shared lane markings, also known as sharrows, and related signage for two-way travel.
Bike Lane | Bike Lane Curbside | A bike lane is a 5-foot-wide area on the roadway delineated by two parallel white pavement markings. Bike lanes can be against the curb or between a row of parked cars and a motor vehicle travel lane. This tab can be used where the bike lane is against the curb, WITHOUT on-street parking, on one side of the street.
Bike Lane | Bike Lanes Curbside | A bike lane is a 5-foot-wide area on the roadway delineated by two parallel white pavement markings. Bike lanes can be against the curb or between a row of parked cars and a motor vehicle travel lane. This tab can be used where the bike lane is against the curb, WITHOUT on-street parking, on two sides of the street.
Bike Lane | Bike Lane w Parking | A bike lane is a 5-foot-wide area on the roadway delineated by two parallel white pavement markings. Bike lanes can be against the curb or between a row of parked cars and a motor vehicle travel lane. This tab can be used where the bike lane is against the curb, WITH on-street parking, on one side of the street.
Bike Lane | Bike Lanes w Parking | A bike lane is a 5-foot-wide area on the roadway delineated by two parallel white pavement markings. Bike lanes can be against the curb or between a row of parked cars and a motor vehicle travel lane. This tab can be used where the bike lane is against the curb, WITH on-street parking, on two sides of the street.
Buffered Bike Lane | Buffer Bike Lane Curbside | A bike lane can be separated from motor vehicle travel lanes by a striped buffer. The buffer allows for additional roadway space between bicycle traffic and motor vehicle traffic. Buffers are at least three-feet-wide and may have vertical delineators, such as flex posts, bollards or planters, to provide additional definition to the bicycle area of travel. This tab accounts for buffered bike lane construction on one side of a roadway. While buffered bike lanes may be located between a row of on-street parking and a motor vehicle travel lane, this configuration allows motor vehicle traffic to encroach on the bicycle area of travel, thus reducing the safety of the bike facility. Due to diminished safety, this estimator does not include calculations for buffered bike lanes between parked vehicles and motor vehicle travel lanes.
Buffered Bike Lane | Buffer Bike Lanes Curbside | A bike lane can be separated from motor vehicle travel lanes by a striped buffer. The buffer allows for additional roadway space between bicycle traffic and motor vehicle traffic. Buffers are at least three-feet-wide and may have vertical delineators, such as flex posts, bollards or planters, to provide additional definition to the bicycle area of travel. This tab accounts for buffered bike lane construction on two sides of a roadway. While buffered bike lanes may be located between a row of on-street parking and a motor vehicle travel lane, this configuration allows motor vehicle traffic to encroach on the bicycle area of travel, thus reducing the safety of the bike facility. Due to diminished safety, this estimator does not include calculations for buffered bike lanes between parked vehicles and motor vehicle travel lanes.
Protected Bike Lane/Cycletrack | Protected Two Way Bike Lane | A protected bike lane is bike lane that has a physical barrier between the bike lane and motor vehicle travel lane. For a single direction protected bike lane, use the BUFFER BIKE LANE CURBSIDE tab. Use this tab for a two-way protected bike lane where two opposing direction bike lanes are located against the curb on one side of the roadway.
Bicycle Boulevard/Neighborhood Greenway | Bike Blvd | A bicycle boulevard, or neighborhood greenway, is a low-traffic-volume, low-traffic-speed roadway with minor roadway adjustments to improve bicycle access. Typically, traffic calming features are applied to a residential corridor to reduce motor vehicle speed and access. This tab includes a variety of traffic calming features that may be included, or excluded. As most bicycle boulevards are on two-way residential roadways, this tab includes information that reflect those conditions.
Shared-use Paths/Paved Trails | Shared-Use Paths | A shared-use path is a two-way, hard surface trail that can be used by both bicyclists and pedestrians. Most shared-use paths have an independent alignment and include most construction items associated with new roadway construction. The design and construction costs of a shared-use paths are closely tied to the physical environment through which they pass. As such, generalized project costs are based on level terrain, rolling terrain, steep terrain and stream valleys.

## INSTRUCTIONS
Planning Level Cost Estimating Tool Instructions
The bicycle project cost estimator is designed to be an 'easy to use' tool. Users enter a few parameters for the intended project and the tool calculates costs based on construction costs and assumed percentage costs for design. These INSTRUCTIONS provide guidance on how to use the tool with descriptions for each field based on a curb side, two-way protected bike lane. Click on a green cell for more information. Additional guidance is provided on various facility tabs as needed.
Planning Level Cost Estimates for Curb Side ,Two-Way Protected Bike Lane On One Side of Roadway
Project Description (Optional)
| Characteristics |  |  | Quantity
| Length | Linear Feet |  | 7920
| Length | Miles |  | 1.5
| Intersections | Each |  | 35
| Intersection Width (Avg) | Linear Feet |  | 40
| Pavement Markings |  |  | Quantity | Unit Cost
| Bike Lane symbols | Each |  | 122.8 | 500 | 61400
| 5" White Retroreflective Pavement Marking | Linear Feet |  | 6520 | 20 | 130400
| 5" White Retroreflective Pavement Marking for 3' Buffer, 10' Spacing | Linear Feet |  | 2771 | 20 | 55420
| 5" Yellow Retroreflective Pavement Marking | Linear Feet |  | 0 | 20 | 0
| Green Pavement Marking | Square Foot |  | 12600 | 20 | 252000
| Signs | Dimensions | Square Footage | Quantity | Unit Cost
| R3-17 (Bike Lane) | 24" x 18" | 3 | 4030 | 50 | 604500
| Rd-17aP (Bike Lane Ahead) | 24" x 8" | 1.3 | 2 | 50 | 130
| Rd-17bP (Bike Lane Ends) | 24" x 8" | 1.3 | 2 | 50 | 130
| R4-4 (Right Turn Yield to Bikes) | 36" x 30" | 7.5 | 35 | 50 | 13125
| R4-11 (Bikes May Use Full Lane) | 30" x 30" | 6.25 | 0 | 50 | 0
| Separation |  | Passive Unit Cost | Quantity | Active Unit Cost
| Flex posts (10' spacing) | Each | 50 | 722 | 50 | 36100
| Low profile, pre-fab concrete barrier (10' length, 50' spacing) | Each | 1000 | 108.6667 | 0 | 0
| Concrete Planters (6' length, 25' spacing) | Each | 1250 | 245.3226 | 0 | 0
| Raised concrete median | Square Foot | 100 | 19560 | 0 | 0
| Construction Subtotal |  |  |  |  | 1153205
| Mobilization | 10% of Construction Costs |  |  | 10% | 115320.5
| Subtotal |  |  |  |  | 1268525.5
| Contingency | 10% of Construction Costs |  |  | 10% | 126852.55
| Construction Subtotal |  |  |  |  | 1395378.05
| Design & Permitting | 25% of Construction Costs |  |  | 25% | 348844.5125
| Preliminary Site Investigation | 5% of Design |  |  | 5% | 17442.2256
| Project Costs |  |  |  |  | 1761664.7881

## Shared Lane
Planning Level Cost Estimates for Shared Lanes on One Side of Roadway | [5 empty] | Instructions: Enter data in these cells. Some cells may have additional information if you click on them.
Project Description
Characteristics |  |  | Quantity
Length | Linear Feet |  | 7920
Length | Miles |  | 1.5
Intersections | Each |  | 12
Intersection Width (Avg) | Linear Feet |  | 40
Pavement Markings |  |  | Quantity | Unit Cost
Shared Lanes symbols | Each |  | 38.4 | 500 | 19200
5" White Retroreflective Pavement Marking | Linear Feet |  | 0 | 20 | 0
5" Yellow Retroreflective Pavement Marking | Linear Feet |  | 0 | 20 | 0
Signs | Dimensions | Square Footage | Quantity | Unit Cost
R3-17 (Bike Lane) | 24" x 18" | 3 | 15 | 50 | 2250
Rd-17aP (Bike Lane Ahead) | 24" x 8" | 1.3 | 0 | 50 | 0
Rd-17bP (Bike Lane Ends) | 24" x 8" | 1.3 | 0 | 50 | 0
R4-4 (Right Turn Yield to Bikes) | 36" x 30" | 7.5 | 12 | 50 | 4500
R4-11 (Bikes May Use Full Lane) | 30" x 30" | 6.25 | 0 | 50 | 0
Construction Subtotal |  |  |  |  | 25950
Mobilization | 10% of Construction Costs |  |  | 10% | 2595
Subtotal |  |  |  |  | 28545
Contingency | 10% of Construction Costs |  |  | 10% | 2854.5
Construction Subtotal |  |  |  |  | 31399.5
Design & Permitting | 25% of Construction Costs |  |  | 25% | 7849.875
Preliminary Site Investigation | 5% of Design |  |  | 5% | 392.4938
Project Costs |  |  |  |  | 39641.8688

## Shared Lanes
Planning Level Cost Estimates for Shared Lanes on Two Sides of Roadway | [5 empty] | Instructions: Enter data in these cells. Some cells may have additional information if you click on them.
Project Description
Characteristics |  |  | Quantity
Length | Linear Feet |  | 7920
Length | Miles |  | 1.5
Intersections | Each |  | 12
Intersection Width (Avg) | Linear Feet |  | 40
Pavement Markings |  |  | Quantity | Unit Cost
Shared Lanes symbols | Each |  | 64.8 | 500 | 32400
5" White Retroreflective Pavement Marking | Linear Feet |  | 0 | 20 | 0
5" Yellow Retroreflective Pavement Marking | Linear Feet |  | 0 | 20 | 0
Signs | Dimensions | Square Footage | Quantity | Unit Cost
R3-17 (Bike Lane) | 24" x 18" | 3 | 18 | 50 | 2700
Rd-17aP (Bike Lane Ahead) | 24" x 8" | 1.3 | 0 | 50 | 0
Rd-17bP (Bike Lane Ends) | 24" x 8" | 1.3 | 0 | 50 | 0
R4-4 (Right Turn Yield to Bikes) | 36" x 30" | 7.5 | 0 | 50 | 0
R4-11 (Bikes May Use Full Lane) | 30" x 30" | 6.25 | 12 | 50 | 3750
Construction Subtotal |  |  |  |  | 38850
Mobilization | 10% of Construction Costs |  |  | 10% | 3885
Subtotal |  |  |  |  | 42735
Contingency | 10% of Construction Costs |  |  | 10% | 4273.5
Construction Subtotal |  |  |  |  | 47008.5
Design & Permitting | 25% of Construction Costs |  |  | 25% | 11752.125
Preliminary Site Investigation | 5% of Design |  |  | 5% | 587.6063
Project Costs |  |  |  |  | 59348.2312

## Bike Lane Curbside
Planning Level Cost Estimates for Curb Side Bike Lane On One Side of Roadway | [5 empty] | Instructions: Enter data in these cells. Some cells may have additional information if you click on them.
Project Description
Characteristics |  |  | Quantity
Length | Linear Feet |  | 7920
Length | Miles |  | 1.5
Intersections | Each |  | 12
Intersection Width (Avg) | Linear Feet |  | 40
Pavement Markings |  |  | Quantity | Unit Cost
Bike Lane symbols | Each |  | 38.4 | 500 | 19200
5" White Retroreflective Pavement Marking | Linear Feet |  | 7440 | 20 | 148800
5" Yellow Retroreflective Pavement Marking | Linear Feet |  | 0 | 20 | 0
Green Pavement Marking | Square Foot |  | 2880 | 20 | 57600
Signs | Dimensions | Square Footage | Quantity | Unit Cost
R3-17 (Bike Lane) | 24" x 18" | 3 | 17 | 50 | 2550
Rd-17aP (Bike Lane Ahead) | 24" x 8" | 1.3 | 0 | 50 | 0
Rd-17bP (Bike Lane Ends) | 24" x 8" | 1.3 | 0 | 50 | 0
R4-4 (Right Turn Yield to Bikes) | 36" x 30" | 7.5 | 12 | 50 | 4500
R4-11 (Bikes May Use Full Lane) | 30" x 30" | 6.25 | 0 | 50 | 0
Construction Subtotal |  |  |  |  | 232650
Mobilization | 10% of Construction Costs |  |  | 10% | 23265
Subtotal |  |  |  |  | 255915
Contingency | 10% of Construction Costs |  |  | 10% | 25591.5
Construction Subtotal |  |  |  |  | 281506.5
Design & Permitting | 25% of Construction Costs |  |  | 25% | 70376.625
Preliminary Site Investigation | 10% of Design |  |  | 10% | 7037.6625
Project Costs |  |  |  |  | 358920.7875

## Bike Lanes Curbside
Planning Level Cost Estimates for Curb Side Bike Lanes on Both Sides of Roadway | [5 empty] | Instructions: Enter data in these cells. Some cells may have additional information if you click on them.
Project Description
Characteristics |  |  | Quantity
Length | Linear Feet |  | 5280
Length | Miles |  | 1
Intersections | Each |  | 15
Intersection Width (Avg) | Linear Feet |  | 30
Pavement Markings |  |  | Quantity | Unit Cost
Bike Lane symbols | Each |  | 50.2 | 500 | 25100
5" White Retroreflective Pavement Marking | Linear Feet |  | 4830 | 20 | 96600
5" Yellow Retroreflective Pavement Marking | Linear Feet |  | 0 | 20 | 0
Green Pavement Marking | Square Foot |  | 9000 | 20 | 180000
Signs | Dimensions | Square Footage | Quantity | Unit Cost
R3-17 (Bike Lane) | 24" x 18" | 3 | 21 | 50 | 3150
Rd-17aP (Bike Lane Ahead) | 24" x 8" | 1.3 | 0 | 50 | 0
Rd-17bP (Bike Lane Ends) | 24" x 8" | 1.3 | 0 | 50 | 0
R4-4 (Right Turn Yield to Bikes) | 36" x 30" | 7.5 | 60 | 50 | 22500
R4-11 (Bikes May Use Full Lane) | 30" x 30" | 6.25 | 0 | 50 | 0
Construction Subtotal |  |  |  |  | 327350
Mobilization | 10% of Construction Costs |  |  | 10% | 32735
Subtotal |  |  |  |  | 360085
Contingency | 10% of Construction Costs |  |  | 10% | 36008.5
Construction Subtotal |  |  |  |  | 396093.5
Design & Permitting | 25% of Construction Costs |  |  | 25% | 99023.375
Preliminary Site Investigation | 10% of Design |  |  | 10% | 9902.3375
Project Costs |  |  |  |  | 505019.2125

## Bike Lane w Parking
Planning Level Cost Estimates for Bike Lane Against Parking Lane on One Side of Roadway | [5 empty] | Instructions: Enter data in these cells. Some cells may have additional information if you click on them.
Project Description
Characteristics |  |  | Quantity
Length | Linear Feet |  | 7920
Length | Miles |  | 1.5
Intersections | Each |  | 12
Intersection Width (Avg) | Linear Feet |  | 40
Pavement Markings |  |  | Quantity | Unit Cost
Bike Lane symbols | Each |  | 38.4 | 500 | 19200
5" White Retroreflective Pavement Marking | Linear Feet |  | 15360 | 20 | 307200
5" Yellow Retroreflective Pavement Marking | Linear Feet |  | 0 | 20 | 0
Green Pavement Marking | Square Foot |  | 4320 | 20 | 86400
Signs | Dimensions | Square Footage | Quantity | Unit Cost
R3-17 (Bike Lane) | 24" x 18" | 3 | 17 | 50 | 2550
Rd-17aP (Bike Lane Ahead) | 24" x 8" | 1.3 | 0 | 50 | 0
Rd-17bP (Bike Lane Ends) | 24" x 8" | 1.3 | 0 | 50 | 0
R4-4 (Right Turn Yield to Bikes) | 36" x 30" | 7.5 | 12 | 50 | 4500
R4-11 (Bikes May Use Full Lane) | 30" x 30" | 6.25 | 0 | 50 | 0
Construction Subtotal |  |  |  |  | 419850
Mobilization | 10% of Construction Costs |  |  | 10% | 41985
Subtotal |  |  |  |  | 461835
Contingency | 10% of Construction Costs |  |  | 10% | 46183.5
Construction Subtotal |  |  |  |  | 508018.5
Design & Permitting | 25% of Construction Costs |  |  | 25% | 127004.625
Preliminary Site Investigation | 10% of Design |  |  | 10% | 12700.4625
Project Costs |  |  |  |  | 647723.5875

## Bike Lanes w Parking
Planning Level Cost Estimates for Bike Lanes Against Parking Lane on Two Sides of Roadway | [5 empty] | Instructions: Enter data in these cells. Some cells may have additional information if you click on them.
Project Description
Characteristics |  |  | Quantity
Length | Linear Feet |  | 7920
Length | Miles |  | 1.5
Intersections | Each |  | 12
Intersection Width (Avg) | Linear Feet |  | 40
Pavement Markings |  |  | Quantity | Unit Cost
Bike Lane symbols | Each |  | 64.8 | 500 | 32400
5" White Retroreflective Pavement Marking | Linear Feet |  | 31200 | 20 | 624000
5" Yellow Retroreflective Pavement Marking | Linear Feet |  | 0 | 20 | 0
Green Pavement Marking | Square Foot |  | 8640 | 20 | 172800
Signs | Dimensions | Square Footage | Quantity | Unit Cost
R3-17 (Bike Lane) | 24" x 18" | 3 | 20 | 50 | 3000
Rd-17aP (Bike Lane Ahead) | 24" x 8" | 1.3 | 0 | 50 | 0
Rd-17bP (Bike Lane Ends) | 24" x 8" | 1.3 | 0 | 50 | 0
R4-4 (Right Turn Yield to Bikes) | 36" x 30" | 7.5 | 24 | 50 | 9000
R4-11 (Bikes May Use Full Lane) | 30" x 30" | 6.25 | 0 | 50 | 0
Construction Subtotal |  |  |  |  | 841200
Mobilization | 10% of Construction Costs |  |  | 10% | 84120
Subtotal |  |  |  |  | 925320
Contingency | 10% of Construction Costs |  |  | 10% | 92532
Construction Subtotal |  |  |  |  | 1017852
Design & Permitting | 25% of Construction Costs |  |  | 25% | 254463
Preliminary Site Investigation | 10% of Design |  |  | 10% | 25446.3
Project Costs |  |  |  |  | 1297761.3

## Buffer Bike Lane Curbside
Planning Level Cost Estimates for Curb Side Buffered Bike Lane On One Side of Roadway | [5 empty] | Instructions: Enter data in these cells. Some cells may have additional information if you click on them.
Project Description
Characteristics |  |  | Quantity
Length | Linear Feet |  | 7920
Length | Miles |  | 1.5
Intersections | Each |  | 12
Intersection Width (Avg) | Linear Feet |  | 40
Pavement Markings |  |  | Quantity | Unit Cost
Bike Lane symbols | Each |  | 38.4 | 500 | 19200
5" White Retroreflective Pavement Marking | Linear Feet |  | 7440 | 20 | 148800
5" White Retroreflective Pavement Marking for 3' Buffer, 10' Spacing | Linear Feet |  | 7920 | 20 | 158400
5" Yellow Retroreflective Pavement Marking | Linear Feet |  | 0 | 20 | 0
Green Pavement Marking | Square Foot |  | 4320 | 20 | 86400
Signs | Dimensions | Square Footage | Quantity | Unit Cost
R3-17 (Bike Lane) | 24" x 18" | 3 | 17 | 50 | 2550
Rd-17aP (Bike Lane Ahead) | 24" x 8" | 1.3 | 0 | 50 | 0
Rd-17bP (Bike Lane Ends) | 24" x 8" | 1.3 | 0 | 50 | 0
R4-4 (Right Turn Yield to Bikes) | 36" x 30" | 7.5 | 12 | 50 | 4500
R4-11 (Bikes May Use Full Lane) | 30" x 30" | 6.25 | 0 | 50 | 0
Separation |  | Passive Unit Cost | Quantity | Active Unit Cost (select only one separation type's passive unit cost to apply here)
Flex posts (10' spacing) | Each | 50 | 744 | 0 | 0
Low profile, pre-fab concrete barrier (10' length, 50' spacing) | Each | 1000 | 124 | 0 | 0
Concrete Planters (6' length, 25' spacing) | Each | 1250 | 240 | 0 | 0
Construction Subtotal |  |  |  |  | 419850
Mobilization | 10% of Construction Costs |  |  | 10% | 41985
Subtotal |  |  |  |  | 461835
Contingency | 10% of Construction Costs |  |  | 10% | 46183.5
Construction Subtotal |  |  |  |  | 508018.5
Design & Permitting | 25% of Construction Costs |  |  | 25% | 127004.625
Preliminary Site Investigation | 10% of Design |  |  | 10% | 12700.4625
Project Costs |  |  |  |  | 647723.5875

## Buffer Bike Lanes Curbside
Planning Level Cost Estimates for Curb Side Buffered Bike Lane On Two Sides of Roadway | [5 empty] | Instructions: Enter data in these cells. Some cells may have additional information if you click on them.
Project Description
Characteristics |  |  | Quantity
Length | Linear Feet |  | 7920
Length | Miles |  | 1.5
Intersections | Each |  | 12
Intersection Width (Avg) | Linear Feet |  | 40
Pavement Markings |  |  | Quantity | Unit Cost
Bike Lane symbols | Each |  | 38.4 | 500 | 19200
5" White Retroreflective Pavement Marking | Linear Feet |  | 15360 | 20 | 307200
5" White Retroreflective Pavement Marking for 3' Buffer, 10' Spacing | Linear Feet |  | 15840 | 20 | 316800
5" Yellow Retroreflective Pavement Marking | Linear Feet |  | 0 | 20 | 0
Green Pavement Marking | Square Foot |  | 8640 | 20 | 172800
Signs | Dimensions | Square Footage | Quantity | Unit Cost
R3-17 (Bike Lane) | 24" x 18" | 3 | 20 | 50 | 3000
Rd-17aP (Bike Lane Ahead) | 24" x 8" | 1.3 | 0 | 50 | 0
Rd-17bP (Bike Lane Ends) | 24" x 8" | 1.3 | 0 | 50 | 0
R4-4 (Right Turn Yield to Bikes) | 36" x 30" | 7.5 | 24 | 50 | 9000
R4-11 (Bikes May Use Full Lane) | 30" x 30" | 6.25 | 0 | 50 | 0
Separation |  | Passive Unit Cost | Quantity | Active Unit Cost (select only one separation type's passive unit cost to apply here)
Flex posts (10' spacing) | Each | 50 | 3072 |  | 0
Low profile, pre-fab concrete barrier (10' length, 50' spacing) | Each | 1000 | 512 |  | 0
Concrete Planters (6' length, 25' spacing) | Each | 1250 | 990.9677 |  | 0
Construction Subtotal |  |  |  |  | 828000
Mobilization | 10% of Construction Costs |  |  | 10% | 82800
Subtotal |  |  |  |  | 910800
Contingency | 10% of Construction Costs |  |  | 10% | 91080
Construction Subtotal |  |  |  |  | 1001880
Design & Permitting | 25% of Construction Costs |  |  | 25% | 250470
Preliminary Site Investigation | 10% of Design |  |  | 10% | 25047
Project Costs |  |  |  |  | 1277397

## Protected Two Way Bike Lane
Planning Level Cost Estimates for Curb Side Two-Way Protected Bike Lane On One Side of Roadway | [5 empty] | Instructions: Enter data in these cells. In some instances, cells may be locked but provide additional information.
Project Description
Characteristics |  |  | Quantity
Length | Linear Feet |  | 7392
Length | Miles |  | 1.4
Intersections | Each |  | 20
Intersection Width (Avg) | Linear Feet |  | 40
Pavement Markings |  |  | Quantity | Unit Cost
Bike Lane symbols | Each |  | 69.28 | 500 | 34640
5" White Retroreflective Pavement Marking | Linear Feet |  | 6592 | 20 | 131840
5" White Retroreflective Pavement Marking for 3' Buffer, 10' Spacing | Linear Feet |  | 7392 | 20 | 147840
5" Yellow Retroreflective Pavement Marking | Linear Feet |  | 0 | 20 | 0
Green Pavement Marking | Square Foot |  | 14400 | 20 | 288000
Signs | Dimensions | Square Footage | Quantity | Unit Cost
R3-17 (Bike Lane) | 24" x 18" | 3 | 24.8 | 50 | 3720
Rd-17aP (Bike Lane Ahead) | 24" x 8" | 1.3 | 0 | 50 | 0
Rd-17bP (Bike Lane Ends) | 24" x 8" | 1.3 | 0 | 50 | 0
R4-4 (Right Turn Yield to Bikes) | 36" x 30" | 7.5 | 20 | 50 | 7500
R4-11 (Bikes May Use Full Lane) | 30" x 30" | 6.25 | 0 | 50 | 0
Separation |  | Passive Unit Cost | Quantity | Active Unit Cost (select only one separation type's passive unit cost to apply here)
Flex posts (10' spacing) | Each | 50 | 699.2 | 0 | 0
Low profile, pre-fab concrete barrier (10' length, 50' spacing) | Each | 1000 | 109.8667 | 0 | 0
Concrete Planters (6' length, 25' spacing) | Each | 1250 | 232.6452 | 0 | 0
Raised concrete median | Square Foot | 100 | 19776 | 0 | 0
Signalization |  |  | Quantity | Per Intersection
Full Intersection(s) |  |  | 0 | 150000 | 0
Patrial Intersection(s) |  |  | 0 | 50000 | 0
Additional Features |  |  | Quantity | Unit Cost
Curb Extensions | Per Intersection |  | 0 | 20000 | 0
Landscaped Chicanes | Each |  | 0 | 7500 | 0
Raised Crosswalk | Each |  | 0 | 10000 | 0
Bicycle-friendly storm grates | Each |  | 0 | 7500 | 0
Construction Subtotal |  |  |  |  | 613540
Mobilization | 10% of Construction Costs |  |  | 10% | 61354
Subtotal |  |  |  |  | 674894
Contingency | 10% of Construction Costs |  |  | 10% | 67489.4
Construction Subtotal |  |  |  |  | 742383.4
Design & Permitting | 25% of Construction Costs |  |  | 25% | 185595.85
Preliminary Site Investigation | 10% of Design |  |  | 10% | 18559.585
Project Costs |  |  |  |  | 946538.835

## Bike Blvd
Planning Level Cost Estimates for Bicycle Boulevard/Neighborhood Greenway Corridor Improvements | [5 empty] | Instructions: Enter data in these cells. In some instances, cells may be locked but provide additional information.
Project Description
Characteristics |  |  | Quantity
Length | Linear Feet |  | 8976
Length | Miles |  | 1.7
Intersections | Each |  | 21
Intersection Width (Avg) | Linear Feet |  | 40
Contraflow Length | Linear Feet |  | 100
Contraflow Intersections | Each |  | 2
Pavement Markings |  |  | Quantity | Unit Cost
Shared Lanes symbols | Each |  | 80.84 | 500 | 40420
5" White Retroreflective Pavement Marking | Linear Feet |  | 0 | 20 | 0
5" Yellow Retroreflective Pavement Marking | Linear Feet |  | 200 | 20 | 4000
Green Pavement Marking | Square Foot |  | 720 | 20 | 14400
Signs | Dimensions | Square Footage | Quantity | Unit Cost
R3-17 (Bike Lane) | 24" x 18" | 3 | 4.3333 | 50 | 650
Rd-17aP (Bike Lane Ahead) | 24" x 8" | 1.3 | 0 | 50 | 0
Rd-17bP (Bike Lane Ends) | 24" x 8" | 1.3 | 0 | 50 | 0
R4-4 (Right Turn Yield to Bikes) | 36" x 30" | 7.5 | 0 | 50 | 0
R4-11 (Bikes May Use Full Lane) | 30" x 30" | 6.25 | 21 | 50 | 6562.5
Traffic Calming Features |  | Passive Unit Cost | Quantity | Active Unit Cost (select only one separation type's passive unit cost to apply here)
Flex posts (10' spacing) for contraflow lane | Each | 50 | 14 | 50 | 700
Flex posts (10' spacing) for additional use | Each | 50 | 0 | 50 | 0
Bicycle-friendly speed humps | Each | 5000 | 0 | 5000 | 0
Curb Extensions | Per Intersection | 20000 | 0 | 20000 | 0
Landscaped Chicanes | Each | 7500 | 0 | 7500 | 0
Raised Crosswalk | Each | 10000 | 0 | 10000 | 0
Raised Intersection | Each | 50000 | 0 | 50000 | 0
Mini-Roundabout | Per Intersection | 50000 | 0 | 50000 | 0
Bicycle-friendly storm grates | Each | 7500 | 0 | 7500 | 0
Construction Subtotal |  |  |  |  | 66732.5
Mobilization | 10% of Construction Costs |  |  | 10% | 6673.25
Subtotal |  |  |  |  | 73405.75
Contingency | 10% of Construction Costs |  |  | 10% | 7340.575
Construction Subtotal |  |  |  |  | 80746.325
Design & Permitting | 25% of Construction Costs |  |  | 25% | 20186.5812
Preliminary Site Investigation | 10% of Design |  |  | 10% | 2018.6581
Project Costs |  |  |  |  | 102951.5644

## Shared-Use Paths
Planning Level Cost Estimates for Shared-use Paths
Project Description
Facility Type | Context | Length (feet) | Length (Miles) | Trail Base Cost per mile | Total Cost per mile
Shared-use Path | Stream Valley | 0 | 0 | 1750000 | 0
| Steep terrain | 0 | 0 | 2500000 | 0
| Rolling Terrain | 0 | 0 | 1250000 | 0
| Level Terrain | 36432 | 6.9 | 1100000 | 7590000
Subtotal |  |  | 6.9 |  | 7590000
Pervious Pavement |  | No |  | 0.5
Subtotal |  |  |  |  | 7590000
Retaining Walls |  | Length (feet) | Length (Miles) | Retaining Wall Cost ($100 per square foot)
| Wall 1 | 0 | 0 | 100 | 0
| Wall 2 | 0 | 0 | 0 | 0
| Wall 3 | 0 | 0 | 0 | 0
Bridges |  | Length (feet) | Length (Miles) | Bridges Cost (per square foot)
| Bridge 1 | 0 | 0 | 400 | 0
| Bridge 2 | 0 | 0 | 400 | 0
| Pre-fabricated Bridge 1 | 0 | 0 | 125 | 0
| Pre-fabricated Bridge 2 | 0 | 0 | 125 | 0
Boardwalk |  | Length (feet) | Length (Miles) | Boardwalk Cost ($45-$150 per square foot)
| Boardwalk 1 | 0 | 0 | 45 | 0
| Boardwalk 2 (w raillings) | 250 | 0.047348 | 150 | 525000
|  | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0
Tunnels |  | Length (feet) | Length (Miles) | Tunnel Cost ($2600 per square foot)
| Tunnel 1 | 0 | 0 | 2600 | 0
| Tunnel 2 | 0 | 0 | 400 | 0
Lighting |  | Length (feet) | Length (Miles) | Lighting Cost ($1m per linear mile)
| Section 1 | 500 | 0.094697 | 1000000 | 94696.9697
| Section 2 | 0 | 0 | 1000000 | 0
Railroad Protection Services |  | Locations |  | $750,000 per Location
| Location | 0 |  | 750000 | 0
Construction Subtotal |  |  |  |  | 8209696.9697
Mobilization | 10% of Construction Costs |  |  | 10% | 820969.697
Subtotal |  |  |  |  | 9030666.6667
Contingency | 30% of Construction Costs |  |  | 30% | 2709200
Construction Subtotal |  |  |  |  | 11739866.6667
Design & Permitting | 25% of Construction Costs | 0.25 |  | 25% | 2934966.6667
Preliminary Site Investigation | 10% of Design | 0.15 |  | 10% | 293496.6667
Project Costs |  |  |  |  | 14968330