## INTRO
Planning Level Cost Estimating Tool For Bicycle Infrastructure Projects
This planning level cost estimating tool has been developed by the Maryland Department of Transportation and the Baltimore Regional Transportation Board's Bicycle and Pedestrian Advisory Group. The purpose of this estimator is to provide guidance to local jurisdictions on project design and construction costs associated with bicycle infrastructure. Cost estimates within this tool are developed by identifying pay items and establishing generalized quantities. This tool aims to cover a wide range of possible expenses that are typically incurred with bicycle projects, but cannot account for all possible items. To account for increased costs as design progresses, a 30% continency is included to allow for items not yet designed. The cost estimator is also provided as a general planning tool to compare costs from planning, develpoment and engineering professionals.
The cost estimating tool is based on American Association of State Highway Transportation Officials (AASHTO) and Maryland Manual of Uniformed Traffic Control Devices (MDMUTCD) standards for facility design, pavement markings, sign placement and other standards. The standards are incorporated into quantity calculations based on the project length and other user preferences.
The cost estimating tool is incorporates quantity formulas based on the project specifics. Users only need to input data into the orange fieds (project length, the number of intersections and average intersction width) to calcuate the remaining costs.
As no two bicycle facilities are exactly alike, this tool is divided into bicycle facility types to allow for more accurate estimates. Each facility type is located on separate tabs. The below TABLE OF CONTENTS list varying bicycle facilities and descriptions to help identify the appropriate facility to use.
Note that this estimator includes generalized costs for asphalt, concrete, grading, drainage improvements, limited utility relocation, pavement markings, signs and traffic signal adjustments. The estimate does not include construction management, special site remediation or the cost for ongoing maintenance. A cost range has been assigned to some general categories; however, these costs can vary widely depending on the exact details and nature of the work. The overall estimates are intended to be general and used for planning purposes. Construction costs will vary based on the ultimate project scope, implementation schedule, and economic conditions at the time of construction.
Additional Costs Associated with Construction Projects
In addition to design and construction costs, various costs are associated with capital project preparation. These costs include preparing environmental documentation, performing a hydrologic and hydraulic study and establishing easements or acquiring properties, identifying historic or cultural resources, endangered species or contaminated site remediation.
For shared-use path projects that include lighting, coordination for the installation, maintenance, operation and expenditure needs to be coordinated among stakeholders. Metering and billing are critical items which need to be determined prior to the lighting design.
Planning level cost estimates aim to cover a wide range of possible expenses that are typically incurred with projects, but cannot account for all possible items. The cost estimator is also provided as a general planning tool to compare costs from planning, development and engineering professionals.
2025 cost values are estimated by applying a 9.23% inflation rate to 2022 costs. Infaltion rates were determined by MDOT Capital and Real Estate Inflation Factors (April 2025). 2022 values can be viewed by un-hiding the hidden columns on each tab. Last updated August 2025.

## Table of Contents
Planning Level Cost Estimating Tool For Bicycle Infrastructure Projects
Table of Contents
Bicycle Facility Type | Tab | Description
Shared Lane | Shared Lane | A shared lane is represented by conditions where bicycle traffic shares a travel lane with motor vehicle traffic. While a shared lane is not a dedicated bicycle facility, the tab accounts for shared lane markings, also known as sharrows, and related signage for one travel direction.
Shared Lane | Shared Lanes | A shared lane is represented by conditions where bicycle traffic shares a travel lane with motor vehicle traffic. While a shared lane is not a dedicated bicycle facility, the tab accounts for shared lane markings, also known as sharrows, and related signage for two-way travel.
Bike Lane | Bike Lane Curbside | A bike lane is a 5-foot-wide area on the roadway delineated by two parallel white pavement markings. Bike lanes can be against the curb or between a row of parked cars and a motor vehicle travel lane. This tab can be used where the bike lane is against the curb, WITHOUT on-street parking, on one side of the street.
Bike Lane | Bike Lanes Curbside | A bike lane is a 5-foot-wide area on the roadway delineated by two parallel white pavement markings. Bike lanes can be against the curb or between a row of parked cars and a motor vehicle travel lane. This tab can be used where the bike lane is against the curb, WITHOUT on-street parking, on two sides of the street.
Bike Lane | Bike Lane w Parking | A bike lane is a 5-foot-wide area on the roadway delineated by two parallel white pavement markings. Bike lanes can be against the curb or between a row of parked cars and a motor vehicle travel lane. This tab can be used where the bike lane is against the curb, WITH on-street parking, on one side of the street.
Bike Lane | Bike Lanes w Parking | A bike lane is a 5-foot-wide area on the roadway delineated by two parallel white pavement markings. Bike lanes can be against the curb or between a row of parked cars and a motor vehicle travel lane. This tab can be used where the bike lane is against the curb, WITH on-street parking, on two sides of the street.
Buffered Bike Lane | Buffer Bike Lane Curbside | A bike lane can be separated from motor vehicle travel lanes by a striped buffer. The buffer allows for additional roadway space between bicycle traffic and motor vehicle traffic. Buffers are at least three-feet-wide and may have vertical delineators, such as flex posts, bollards or planters, to provide additional definition to the bicycle area of travel. This tab accounts for buffered bike lane construction on one side of a roadway. While buffered bike lanes may be located between a row of on-street parking and a motor vehicle travel lane, this configuration allows motor vehicle traffic to encroach on the bicycle area of travel, thus reducing the safety of the bike facility. Due to diminished safety, this estimator does not include calculations for buffered bike lanes between parked vehicles and motor vehicle travel lanes.
Buffered Bike Lane | Buffer Bike Lanes Curbside | A bike lane can be separated from motor vehicle travel lanes by a striped buffer. The buffer allows for additional roadway space between bicycle traffic and motor vehicle traffic. Buffers are at least three-feet-wide and may have vertical delineators, such as flex posts, bollards or planters, to provide additional definition to the bicycle area of travel. This tab accounts for buffered bike lane construction on two sides of a roadway. While buffered bike lanes may be located between a row of on-street parking and a motor vehicle travel lane, this configuration allows motor vehicle traffic to encroach on the bicycle area of travel, thus reducing the safety of the bike facility. Due to diminished safety, this estimator does not include calculations for buffered bike lanes between parked vehicles and motor vehicle travel lanes.
Protected Bike Lane/Cycletrack | Protected Two Way Bike Lane | A protected bike lane is bike lane that has a physical barrier between the bike lane and motor vehicle travel lane. For a single direction protected bike lane, use the BUFFER BIKE LANE CURBSIDE tab. Use this tab for a two-way protected bike lane where two opposing direction bike lanes are located against the curb on one side of the roadway.
Bicycle Boulevard/Neighborhood Greenway | Bike Blvd | A bicycle boulevard, or neighborhood greenway, is a low-traffic-volume, low-traffic-speed roadway with minor roadway adjustments to improve bicycle access. Typically, traffic calming features are applied to a residential corridor to reduce motor vehicle speed and access. This tab includes a variety of traffic calming features that may be included, or excluded. As most bicycle boulevards are on two-way residential roadways, this tab includes information that reflect those conditions.
Shared-use Paths/Paved Trails | Shared-Use Paths | A shared-use path is a two-way, hard surface trail that can be used by both bicyclists and pedestrians. Most shared-use paths have an independent alignment and include most construction items associated with new roadway construction. The design and construction costs of a shared-use paths are closely tied to the physical environment through which they pass. As such, generalized project costs are based on level terrain, rolling terrain, steep terrain and stream valleys.
Complete Streets Intersection Treatements | Complete Streets Intersection | A complete streets intersection is designed for the safety of all users, including pedestrians and bicyclists. This includes temporary treatments, traffic calming, bicycle treatments, and pedestrain safety benefits.

## INSTRUCTIONS
Planning Level Cost Estimating Tool Instructions
The bicycle project cost estimator is designed to be an 'easy to use' tool. Users enter a few parameters for the intended project and the tool calculates costs based on construction costs and assumed percentage costs for design. These INSTRUCTIONS provide guidance on how to use the tool with descriptions for each field based on a curb side, two-way protected bike lane. Click on a green cell for more information. Additional guidance is provided on various facility tabs as needed.
Planning Level Cost Estimates for Curb Side ,Two-Way Protected Bike Lane On One Side of Roadway
Project Description (Optional)
| Characteristics |  |  | Quantity
| Length | Linear Feet |  | 7920
| Length | Miles |  | 1.5
| Intersections | Each |  | 35
| Intersection Width (Avg) | Linear Feet |  | 40
| Pavement Markings |  |  | Quantity | 2022 Unit Cost | 2025 Unit Cost | 2022 Total | 2025 Total
| Bike Lane symbols | Each |  | 122.8 | 500 | 546.15 | 61400 | 67067.22
| 5" White Retroreflective Pavement Marking | Linear Feet |  | 6520 | 20 | 21.846 | 130400 | 142435.92
| 5" White Retroreflective Pavement Marking for 3' Buffer, 10' Spacing | Linear Feet |  | 2771 | 20 | 21.846 | 55420 | 60535.266
| 5" Yellow Retroreflective Pavement Marking | Linear Feet |  | 0 | 20 | 21.846 | 0 | 0
| Green Pavement Marking | Square Foot |  | 12600 | 20 | 21.846 | 252000 | 275259.6
| Signs | Dimensions | Square Footage | Quantity | 2022 Unit Cost | 2025 Unit Cost | 2022 Total | 2025 Total
| R3-17 (Bike Lane) | 24" x 18" | 3 | 4030 | 50 | 54.615 | 604500 | 660295.35
| Rd-17aP (Bike Lane Ahead) | 24" x 8" | 1.3 | 2 | 50 | 54.615 | 130 | 141.999
| Rd-17bP (Bike Lane Ends) | 24" x 8" | 1.3 | 2 | 50 | 54.615 | 130 | 141.999
| R4-4 (Right Turn Yield to Bikes) | 36" x 30" | 7.5 | 35 | 50 | 54.615 | 13125 | 14336.4375
| R4-11 (Bikes May Use Full Lane) | 30" x 30" | 6.25 | 0 | 50 | 54.615 | 0 | 0
| Separation |  | Passive Unit Cost | Quantity | 2022 Active Unit Cost | 2025 Active Unit Cost | 2022 Total | 2025 Total
| Flex posts (10' spacing) | Each | 50 | 722 | 50 | 54.615 | 36100 | 39432.03
| Low profile, pre-fab concrete barrier (10' length, 50' spacing) | Each | 1000 | 108.6667 | 0 | 0 | 0 | 0
| Concrete Planters (6' length, 25' spacing) | Each | 1250 | 245.3226 | 0 | 0 | 0 | 0
| Raised concrete median | Square Foot | 100 | 19560 | 0 | 0 | 0 | 0
| Construction Subtotal | [5 empty] | 1153205 | 1259645.8215
| Mobilization | 10% of Construction Costs |  |  | 10% |  | 115320.5 | 125964.5822
| Subtotal | [5 empty] | 1268525.5 | 1385610.4036
| Contingency | 10% of Construction Costs |  |  | 10% |  | 126852.55 | 138561.0404
| Construction Subtotal | [5 empty] | 1395378.05 | 1524171.444
| Design & Permitting | 25% of Construction Costs |  |  | 25% |  | 348844.5125 | 381042.861
| Preliminary Site Investigation | 5% of Design |  |  | 5% |  | 17442.2256 | 19052.1431
| Project Costs | [5 empty] | 1761664.7881 | 1924266.4481

## Shared Lane
Planning Level Cost Estimates for Shared Lanes on One Side of Roadway | [7 empty] | Instructions: Enter data in these cells. Some cells may have additional information if you click on them.
Project Description
Characteristics |  |  | Quantity
Length | Linear Feet |  | 7920
Length | Miles |  | 1.5
Intersections | Each |  | 12
Intersection Width (Avg) | Linear Feet |  | 40
Pavement Markings |  |  | Quantity | 2022 Unit Cost | 2025 Unit Cost | 2022 Total | 2025 Total
Shared Lanes symbols | Each |  | 38.4 | 500 | 546.15 | 19200 | 20972.16
5" White Retroreflective Pavement Marking | Linear Feet |  | 0 | 20 | 21.846 | 0 | 0
5" Yellow Retroreflective Pavement Marking | Linear Feet |  | 0 | 20 | 21.846 | 0 | 0
Signs | Dimensions | Square Footage | Quantity | 2022 Unit Cost | 2025 Unit Cost | 2022 Total | 2025 Total
R3-17 (Bike Lane) | 24" x 18" | 3 | 15 | 50 | 54.615 | 2250 | 2457.675
Rd-17aP (Bike Lane Ahead) | 24" x 8" | 1.3 | 0 | 50 | 54.615 | 0 | 0
Rd-17bP (Bike Lane Ends) | 24" x 8" | 1.3 | 0 | 50 | 54.615 | 0 | 0
R4-4 (Right Turn Yield to Bikes) | 36" x 30" | 7.5 | 12 | 50 | 54.615 | 4500 | 4915.35
R4-11 (Bikes May Use Full Lane) | 30" x 30" | 6.25 | 0 | 50 | 54.615 | 0 | 0
Construction Subtotal | [5 empty] | 25950 | 28345.185
Mobilization | 10% of Construction Costs |  |  | 10% |  | 2595 | 2834.5185
Subtotal | [5 empty] | 28545 | 31179.7035
Contingency | 10% of Construction Costs |  |  | 10% |  | 2854.5 | 3117.9704
Construction Subtotal | [5 empty] | 31399.5 | 34297.6738
Design & Permitting | 25% of Construction Costs |  |  | 25% |  | 7849.875 | 8574.4185
Preliminary Site Investigation | 5% of Design |  |  | 5% |  | 392.4938 | 428.7209
Project Costs | [5 empty] | 39641.8688 | 43300.8132

## Shared Lanes
Planning Level Cost Estimates for Shared Lanes on Two Sides of Roadway | [7 empty] | Instructions: Enter data in these cells. Some cells may have additional information if you click on them.
Project Description
Characteristics |  |  | Quantity
Length | Linear Feet |  | 7920
Length | Miles |  | 1.5
Intersections | Each |  | 12
Intersection Width (Avg) | Linear Feet |  | 40
Pavement Markings |  |  | Quantity | 2022 Unit Cost | 2025 Unit Cost | 2022 Total | 2025 Total
Shared Lanes symbols | Each |  | 64.8 | 500 | 546.15 | 32400 | 35390.52
5" White Retroreflective Pavement Marking | Linear Feet |  | 0 | 20 | 21.846 | 0 | 0
5" Yellow Retroreflective Pavement Marking | Linear Feet |  | 0 | 20 | 21.846 | 0 | 0
Signs | Dimensions | Square Footage | Quantity | 2022 Unit Cost | 2025 Unit Cost | 2022 Total | 2025 Total
R3-17 (Bike Lane) | 24" x 18" | 3 | 18 | 50 | 54.615 | 2700 | 2949.21
Rd-17aP (Bike Lane Ahead) | 24" x 8" | 1.3 | 0 | 50 | 54.615 | 0 | 0
Rd-17bP (Bike Lane Ends) | 24" x 8" | 1.3 | 0 | 50 | 54.615 | 0 | 0
R4-4 (Right Turn Yield to Bikes) | 36" x 30" | 7.5 | 0 | 50 | 54.615 | 0 | 0
R4-11 (Bikes May Use Full Lane) | 30" x 30" | 6.25 | 12 | 50 | 54.615 | 3750 | 4096.125
Construction Subtotal | [5 empty] | 38850 | 42435.855
Mobilization | 10% of Construction Costs |  |  | 10% |  | 3885 | 4243.5855
Subtotal | [5 empty] | 42735 | 46679.4405
Contingency | 10% of Construction Costs |  |  | 10% |  | 4273.5 | 4667.9441
Construction Subtotal | [5 empty] | 47008.5 | 51347.3846
Design & Permitting | 25% of Construction Costs |  |  | 25% |  | 11752.125 | 12836.8461
Preliminary Site Investigation | 5% of Design |  |  | 5% |  | 587.6063 | 641.8423
Project Costs | [5 empty] | 59348.2312 | 64826.073

## Bike Lane Curbside
Planning Level Cost Estimates for Curb Side Bike Lane On One Side of Roadway | [7 empty] | Instructions: Enter data in these cells. Some cells may have additional information if you click on them.
Project Description
Characteristics |  |  | Quantity
Length | Linear Feet |  | 7920
Length | Miles |  | 1.5
Intersections | Each |  | 12
Intersection Width (Avg) | Linear Feet |  | 40
Pavement Markings |  |  | Quantity | 2022 Unit Cost | 2025 Unit Cost | 2022 Total | 2025 Total
Bike Lane symbols | Each |  | 38.4 | 500 | 546.15 | 19200 | 20972.16
5" White Retroreflective Pavement Marking | Linear Feet |  | 7440 | 20 | 21.846 | 148800 | 162534.24
5" Yellow Retroreflective Pavement Marking | Linear Feet |  | 0 | 20 | 21.846 | 0 | 0
Green Pavement Marking | Square Foot |  | 2880 | 20 | 21.846 | 57600 | 62916.48
Signs | Dimensions | Square Footage | Quantity | 2022 Unit Cost | 2025 Unit Cost | 2022 Total | 2025 Total
R3-17 (Bike Lane) | 24" x 18" | 3 | 17 | 50 | 54.615 | 2550 | 2785.365
Rd-17aP (Bike Lane Ahead) | 24" x 8" | 1.3 | 0 | 50 | 54.615 | 0 | 0
Rd-17bP (Bike Lane Ends) | 24" x 8" | 1.3 | 0 | 50 | 54.615 | 0 | 0
R4-4 (Right Turn Yield to Bikes) | 36" x 30" | 7.5 | 12 | 50 | 54.615 | 4500 | 4915.35
R4-11 (Bikes May Use Full Lane) | 30" x 30" | 6.25 | 0 | 50 | 54.615 | 0 | 0
Construction Subtotal | [5 empty] | 232650 | 254123.595
Mobilization | 10% of Construction Costs |  |  | 10% |  | 23265 | 25412.3595
Subtotal | [5 empty] | 255915 | 279535.9545
Contingency | 10% of Construction Costs |  |  | 10% |  | 25591.5 | 27953.5955
Construction Subtotal | [5 empty] | 281506.5 | 307489.55
Design & Permitting | 25% of Construction Costs |  |  | 25% |  | 70376.625 | 76872.3875
Preliminary Site Investigation | 10% of Design |  |  | 10% |  | 7037.6625 | 7687.2387
Project Costs | [5 empty] | 358920.7875 | 392049.1762

## Bike Lanes Curbside
Planning Level Cost Estimates for Curb Side Bike Lanes on Both Sides of Roadway | [7 empty] | Instructions: Enter data in these cells. Some cells may have additional information if you click on them.
Project Description
Characteristics |  |  | Quantity
Length | Linear Feet |  | 5280
Length | Miles |  | 1
Intersections | Each |  | 15
Intersection Width (Avg) | Linear Feet |  | 30
Pavement Markings |  |  | Quantity | 2022 Unit Cost | 2025 Unit Cost | 2022 Total | 2025 Total
Bike Lane symbols | Each |  | 50.2 | 500 | 546.15 | 25100 | 27416.73
5" White Retroreflective Pavement Marking | Linear Feet |  | 4830 | 20 | 21.846 | 96600 | 105516.18
5" Yellow Retroreflective Pavement Marking | Linear Feet |  | 0 | 20 | 21.846 | 0 | 0
Green Pavement Marking | Square Foot |  | 9000 | 20 | 21.846 | 180000 | 196614
Signs | Dimensions | Square Footage | Quantity | 2022 Unit Cost | 2025 Unit Cost | 2022 Total | 2025 Total
R3-17 (Bike Lane) | 24" x 18" | 3 | 21 | 50 | 54.615 | 3150 | 3440.745
Rd-17aP (Bike Lane Ahead) | 24" x 8" | 1.3 | 0 | 50 | 54.615 | 0 | 0
Rd-17bP (Bike Lane Ends) | 24" x 8" | 1.3 | 0 | 50 | 54.615 | 0 | 0
R4-4 (Right Turn Yield to Bikes) | 36" x 30" | 7.5 | 60 | 50 | 54.615 | 22500 | 24576.75
R4-11 (Bikes May Use Full Lane) | 30" x 30" | 6.25 | 0 | 50 | 54.615 | 0 | 0
Construction Subtotal | [5 empty] | 327350 | 357564.405
Mobilization | 10% of Construction Costs |  |  | 10% |  | 32735 | 35756.4405
Subtotal | [5 empty] | 360085 | 393320.8455
Contingency | 10% of Construction Costs |  |  | 10% |  | 36008.5 | 39332.0845
Construction Subtotal | [5 empty] | 396093.5 | 432652.9301
Design & Permitting | 25% of Construction Costs |  |  | 25% |  | 99023.375 | 108163.2325
Preliminary Site Investigation | 10% of Design |  |  | 10% |  | 9902.3375 | 10816.3233
Project Costs | [5 empty] | 505019.2125 | 551632.4858

## Bike Lane w Parking
Planning Level Cost Estimates for Bike Lane Against Parking Lane on One Side of Roadway | [7 empty] | Instructions: Enter data in these cells. Some cells may have additional information if you click on them.
Project Description
Characteristics |  |  | Quantity
Length | Linear Feet |  | 7920
Length | Miles |  | 1.5
Intersections | Each |  | 12
Intersection Width (Avg) | Linear Feet |  | 40
Pavement Markings |  |  | Quantity | 2022 Unit Cost | 2025 Unit Cost | 2022 Total | 2025 Total
Bike Lane symbols | Each |  | 38.4 | 500 | 546.15 | 19200 | 20972.16
5" White Retroreflective Pavement Marking | Linear Feet |  | 15360 | 20 | 21.846 | 307200 | 335554.56
5" Yellow Retroreflective Pavement Marking | Linear Feet |  | 0 | 20 | 21.846 | 0 | 0
Green Pavement Marking | Square Foot |  | 4320 | 20 | 21.846 | 86400 | 94374.72
Signs | Dimensions | Square Footage | Quantity | 2022 Unit Cost | 2025 Unit Cost | 2022 Total | 2025 Total
R3-17 (Bike Lane) | 24" x 18" | 3 | 17 | 50 | 54.615 | 2550 | 2785.365
Rd-17aP (Bike Lane Ahead) | 24" x 8" | 1.3 | 0 | 50 | 54.615 | 0 | 0
Rd-17bP (Bike Lane Ends) | 24" x 8" | 1.3 | 0 | 50 | 54.615 | 0 | 0
R4-4 (Right Turn Yield to Bikes) | 36" x 30" | 7.5 | 12 | 50 | 54.615 | 4500 | 4915.35
R4-11 (Bikes May Use Full Lane) | 30" x 30" | 6.25 | 0 | 50 | 54.615 | 0 | 0
Construction Subtotal | [5 empty] | 419850 | 458602.155
Mobilization | 10% of Construction Costs |  |  | 10% |  | 41985 | 45860.2155
Subtotal | [5 empty] | 461835 | 504462.3705
Contingency | 10% of Construction Costs |  |  | 10% |  | 46183.5 | 50446.2371
Construction Subtotal | [5 empty] | 508018.5 | 554908.6076
Design & Permitting | 25% of Construction Costs |  |  | 25% |  | 127004.625 | 138727.1519
Preliminary Site Investigation | 10% of Design |  |  | 10% |  | 12700.4625 | 13872.7152
Project Costs | [5 empty] | 647723.5875 | 707508.4746

## Bike Lanes w Parking
Planning Level Cost Estimates for Bike Lanes Against Parking Lane on Two Sides of Roadway | [7 empty] | Instructions: Enter data in these cells. Some cells may have additional information if you click on them.
Project Description
Characteristics |  |  | Quantity
Length | Linear Feet |  | 7920
Length | Miles |  | 1.5
Intersections | Each |  | 12
Intersection Width (Avg) | Linear Feet |  | 40
Pavement Markings |  |  | Quantity | 2022 Unit Cost | 2025 Unit Cost | 2022 Total | 2025 Total
Bike Lane symbols | Each |  | 64.8 | 500 | 546.15 | 32400 | 35390.52
5" White Retroreflective Pavement Marking | Linear Feet |  | 31200 | 20 | 21.846 | 624000 | 681595.2
5" Yellow Retroreflective Pavement Marking | Linear Feet |  | 0 | 20 | 21.846 | 0 | 0
Green Pavement Marking | Square Foot |  | 8640 | 20 | 21.846 | 172800 | 188749.44
Signs | Dimensions | Square Footage | Quantity | 2022 Unit Cost | 2025 Unit Cost | 2022 Total | 2025 Total
R3-17 (Bike Lane) | 24" x 18" | 3 | 20 | 50 | 54.615 | 3000 | 3276.9
Rd-17aP (Bike Lane Ahead) | 24" x 8" | 1.3 | 0 | 50 | 54.615 | 0 | 0
Rd-17bP (Bike Lane Ends) | 24" x 8" | 1.3 | 0 | 50 | 54.615 | 0 | 0
R4-4 (Right Turn Yield to Bikes) | 36" x 30" | 7.5 | 24 | 50 | 54.615 | 9000 | 9830.7
R4-11 (Bikes May Use Full Lane) | 30" x 30" | 6.25 | 0 | 50 | 54.615 | 0 | 0
Construction Subtotal | [5 empty] | 841200 | 918842.76
Mobilization | 10% of Construction Costs |  |  | 10% |  | 84120 | 91884.276
Subtotal | [5 empty] | 925320 | 1010727.036
Contingency | 10% of Construction Costs |  |  | 10% |  | 92532 | 101072.7036
Construction Subtotal | [5 empty] | 1017852 | 1111799.7396
Design & Permitting | 25% of Construction Costs |  |  | 25% |  | 254463 | 277949.9349
Preliminary Site Investigation | 10% of Design |  |  | 10% |  | 25446.3 | 27794.9935
Project Costs | [5 empty] | 1297761.3 | 1417544.668

## Buffer Bike Lane Curbside
Planning Level Cost Estimates for Curb Side Buffered Bike Lane On One Side of Roadway | [7 empty] | Instructions: Enter data in these cells. Some cells may have additional information if you click on them.
Project Description
Characteristics |  |  | Quantity
Length | Linear Feet |  | 7920
Length | Miles |  | 1.5
Intersections | Each |  | 12
Intersection Width (Avg) | Linear Feet |  | 40
Pavement Markings |  |  | Quantity | 2022 Unit Cost | 2025 Unit Cost | 2022 Total | 2025 Total
Bike Lane symbols | Each |  | 38.4 | 500 | 546.15 | 19200 | 20972.16
5" White Retroreflective Pavement Marking | Linear Feet |  | 7440 | 20 | 21.846 | 148800 | 162534.24
5" White Retroreflective Pavement Marking for 3' Buffer, 10' Spacing | Linear Feet |  | 7920 | 20 | 21.846 | 158400 | 173020.32
5" Yellow Retroreflective Pavement Marking | Linear Feet |  | 0 | 20 | 21.846 | 0 | 0
Green Pavement Marking | Square Foot |  | 4320 | 20 | 21.846 | 86400 | 94374.72
Signs | Dimensions | Square Footage | Quantity | 2022 Unit Cost | 2025 Unit Cost | 2022 Total | 2025 Total
R3-17 (Bike Lane) | 24" x 18" | 3 | 17 | 50 | 54.615 | 2550 | 2785.365
Rd-17aP (Bike Lane Ahead) | 24" x 8" | 1.3 | 0 | 50 | 54.615 | 0 | 0
Rd-17bP (Bike Lane Ends) | 24" x 8" | 1.3 | 0 | 50 | 54.615 | 0 | 0
R4-4 (Right Turn Yield to Bikes) | 36" x 30" | 7.5 | 12 | 50 | 54.615 | 4500 | 4915.35
R4-11 (Bikes May Use Full Lane) | 30" x 30" | 6.25 | 0 | 50 | 54.615 | 0 | 0
Separation |  | Passive Unit Cost | Quantity | 2022 Active Unit Cost (select only one separation type's passive unit cost to apply here) | 2025 Active Unit Cost | 2022 Total | 2025 Total
Flex posts (10' spacing) | Each | 50 | 744 | 0 | 0 | 0 | 0
Low profile, pre-fab concrete barrier (10' length, 50' spacing) | Each | 1000 | 124 | 0 | 0 | 0 | 0
Concrete Planters (6' length, 25' spacing) | Each | 1250 | 240 | 0 | 0 | 0 | 0
Construction Subtotal | [5 empty] | 419850 | 0
Mobilization | 10% of Construction Costs |  |  | 10% |  | 41985 | 45860.2155
Subtotal | [5 empty] | 461835 | 504462.3705
Contingency | 10% of Construction Costs |  |  | 10% |  | 46183.5 | 50446.2371
Construction Subtotal | [5 empty] | 508018.5 | 554908.6076
Design & Permitting | 25% of Construction Costs |  |  | 25% |  | 127004.625 | 138727.1519
Preliminary Site Investigation | 10% of Design |  |  | 10% |  | 12700.4625 | 13872.7152
Project Costs | [5 empty] | 647723.5875 | 707508.4746

## Buffer Bike Lanes Curbside
Planning Level Cost Estimates for Curb Side Buffered Bike Lane On Two Sides of Roadway | [7 empty] | Instructions: Enter data in these cells. Some cells may have additional information if you click on them.
Project Description
Characteristics |  |  | Quantity
Length | Linear Feet |  | 7920
Length | Miles |  | 1.5
Intersections | Each |  | 12
Intersection Width (Avg) | Linear Feet |  | 40
Pavement Markings |  |  | Quantity | 2022 Unit Cost | 2025 Unit Cost | 2022 Total | 2025 Total
Bike Lane symbols | Each |  | 38.4 | 500 | 546.15 | 19200 | 20972.16
5" White Retroreflective Pavement Marking | Linear Feet |  | 15360 | 20 | 21.846 | 307200 | 335554.56
5" White Retroreflective Pavement Marking for 3' Buffer, 10' Spacing | Linear Feet |  | 15840 | 20 | 21.846 | 316800 | 346040.64
5" Yellow Retroreflective Pavement Marking | Linear Feet |  | 0 | 20 | 21.846 | 0 | 0
Green Pavement Marking | Square Foot |  | 8640 | 20 | 21.846 | 172800 | 188749.44
Signs | Dimensions | Square Footage | Quantity | 2022 Unit Cost | 2025 Unit Cost | 2022 Total | 2025 Total
R3-17 (Bike Lane) | 24" x 18" | 3 | 20 | 50 | 54.615 | 3000 | 3276.9
Rd-17aP (Bike Lane Ahead) | 24" x 8" | 1.3 | 0 | 50 | 54.615 | 0 | 0
Rd-17bP (Bike Lane Ends) | 24" x 8" | 1.3 | 0 | 50 | 54.615 | 0 | 0
R4-4 (Right Turn Yield to Bikes) | 36" x 30" | 7.5 | 24 | 50 | 54.615 | 9000 | 9830.7
R4-11 (Bikes May Use Full Lane) | 30" x 30" | 6.25 | 0 | 50 | 54.615 | 0 | 0
Separation |  | Passive Unit Cost | Quantity | 2022 Active Unit Cost (select only one separation type's passive unit cost to apply here) | 2025 Active Unit Cost | 2022 Total | 2025 Total
Flex posts (10' spacing) | Each | 50 | 3072 |  | 0 | 0 | 0
Low profile, pre-fab concrete barrier (10' length, 50' spacing) | Each | 1000 | 512 |  | 0 | 0 | 0
Concrete Planters (6' length, 25' spacing) | Each | 1250 | 990.9677 |  | 0 | 0 | 0
Construction Subtotal | [5 empty] | 828000 | 904424.4
Mobilization | 10% of Construction Costs |  |  | 10% |  | 82800 | 90442.44
Subtotal | [5 empty] | 910800 | 994866.84
Contingency | 10% of Construction Costs |  |  | 10% |  | 91080 | 99486.684
Construction Subtotal | [5 empty] | 1001880 | 1094353.524
Design & Permitting | 25% of Construction Costs |  |  | 25% |  | 250470 | 273588.381
Preliminary Site Investigation | 10% of Design |  |  | 10% |  | 25047 | 27358.8381
Project Costs | [5 empty] | 1277397 | 1395300.7431

## Protected Two Way Bike Lane
Planning Level Cost Estimates for Curb Side Two-Way Protected Bike Lane On One Side of Roadway | [7 empty] | Instructions: Enter data in these cells. In some instances, cells may be locked but provide additional information.
Project Description
Characteristics |  |  | Quantity
Length | Linear Feet |  | 7392
Length | Miles |  | 1.4
Intersections | Each |  | 20
Intersection Width (Avg) | Linear Feet |  | 40
Pavement Markings |  |  | Quantity | 2022 Unit Cost | 2025 Unit Cost | 2022 Total | 2025 Total
Bike Lane symbols | Each |  | 69.28 | 500 | 546.15 | 34640 | 37837.272
5" White Retroreflective Pavement Marking | Linear Feet |  | 6592 | 20 | 21.846 | 131840 | 144008.832
5" White Retroreflective Pavement Marking for 3' Buffer, 10' Spacing | Linear Feet |  | 7392 | 20 | 21.846 | 147840 | 161485.632
5" Yellow Retroreflective Pavement Marking | Linear Feet |  | 0 | 20 | 21.846 | 0 | 0
Green Pavement Marking | Square Foot |  | 14400 | 20 | 21.846 | 288000 | 314582.4
Signs | Dimensions | Square Footage | Quantity | 2022 Unit Cost | 2025 Unit Cost | 2022 Total | 2025 Total
R3-17 (Bike Lane) | 24" x 18" | 3 | 24.8 | 50 | 54.615 | 3720 | 4063.356
Rd-17aP (Bike Lane Ahead) | 24" x 8" | 1.3 | 0 | 50 | 54.615 | 0 | 0
Rd-17bP (Bike Lane Ends) | 24" x 8" | 1.3 | 0 | 50 | 54.615 | 0 | 0
R4-4 (Right Turn Yield to Bikes) | 36" x 30" | 7.5 | 20 | 50 | 54.615 | 7500 | 8192.25
R4-11 (Bikes May Use Full Lane) | 30" x 30" | 6.25 | 0 | 50 | 54.615 | 0 | 0
Separation |  | Passive Unit Cost | Quantity | 2022 Active Unit Cost (select only one separation type's passive unit cost to apply here) | 2025 Active Unit Cost | 2022 Total | 2025 Total
Flex posts (10' spacing) | Each | 50 | 699.2 | 0 | 0 | 0 | 0
Low profile, pre-fab concrete barrier (10' length, 50' spacing) | Each | 1000 | 109.8667 | 0 | 0 | 0 | 0
Concrete Planters (6' length, 25' spacing) | Each | 1250 | 232.6452 | 0 | 0 | 0 | 0
Raised concrete median | Square Foot | 100 | 19776 | 0 | 0 | 0 | 0
Signalization |  |  | Quantity | 2022 Per Intersection | 2025 Per Intersection | 2022 Total | 2025 Total
Full Intersection(s) |  |  | 0 | 150000 | 163845 | 0 | 0
Patrial Intersection(s) |  |  | 0 | 50000 | 54615 | 0 | 0
Additional Features |  |  | Quantity | 2022 Unit Cost | 2025 Unit Cost | 2022 Total | 2025 Total
Curb Extensions | Per Intersection |  | 0 | 20000 | 21846 | 0 | 0
Landscaped Chicanes | Each |  | 0 | 7500 | 8192.25 | 0 | 0
Raised Crosswalk | Each |  | 0 | 10000 | 10923 | 0 | 0
Bicycle-friendly storm grates | Each |  | 0 | 7500 | 8192.25 | 0 | 0
Construction Subtotal | [5 empty] | 613540 | 670169.742
Mobilization | 10% of Construction Costs |  |  | 10% |  | 61354 | 67016.9742
Subtotal | [5 empty] | 674894
Contingency | 10% of Construction Costs |  |  | 10% |  | 67489.4 | 73718.6716
Construction Subtotal | [5 empty] | 742383.4 | 810905.3878
Design & Permitting | 25% of Construction Costs |  |  | 25% |  | 185595.85 | 202726.347
Preliminary Site Investigation | 10% of Design |  |  | 10% |  | 18559.585 | 20272.6347
Project Costs | [5 empty] | 946538.835 | 1033904.3695

## Bike Blvd
Planning Level Cost Estimates for Bicycle Boulevard/Neighborhood Greenway Corridor Improvements | [7 empty] | Instructions: Enter data in these cells. In some instances, cells may be locked but provide additional information.
Project Description
Characteristics |  |  | Quantity | Trail 2022 Base Cost per mile | Trail 2025 Base Cost per mile | 2022 Total Cost per mile | 2025 Total Cost per mile
Length | Linear Feet |  | 8976 |  | 0 |  | 0
Length | Miles |  | 1.7 |  | 0 |  | 0
Intersections | Each |  | 21 |  | 0 |  | 0
Intersection Width (Avg) | Linear Feet |  | 40 |  | 0 |  | 0
Contraflow Length | Linear Feet |  | 100 |  |  |  | 0
Contraflow Intersections | Each |  | 2
Pavement Markings |  |  | Quantity | 2022 Unit Cost | 2025 Unit Cost | 2022 Total | 2025 Total
Shared Lanes symbols | Each |  | 80.84 | 500 | 546.15 | 0 | 0
5" White Retroreflective Pavement Marking | Linear Feet |  | 200 | 20 | 21.846 | 4000 | 4369.2
5" Yellow Retroreflective Pavement Marking | Linear Feet |  | 200 | 20 | 21.846 | 4000 | 4369.2
Green Pavement Marking | Square Foot |  | 720 | 20 | 21.846 | 14400 | 15729.12
Signs | Dimensions | Square Footage | Quantity | 2022 Unit Cost | 2025 Unit Cost | 2022 Total | 2025 Total
R3-17 (Bike Lane) | 24" x 18" | 3 | 4.3333 | 50 | 54.615 | 650 | 709.995
Rd-17aP (Bike Lane Ahead) | 24" x 8" | 1.3 | 0 | 50 | 54.615 | 0 | 0
Rd-17bP (Bike Lane Ends) | 24" x 8" | 1.3 | 0 | 50 | 54.615 | 0 | 0
R4-4 (Right Turn Yield to Bikes) | 36" x 30" | 7.5 | 0 | 50 | 54.615 | 0 | 0
R4-11 (Bikes May Use Full Lane) | 30" x 30" | 6.25 | 21 | 50 | 54.615 | 6562.5 | 7168.2188
Traffic Calming Features |  |  | Quantity | 2022 Unit Cost | 2025 Unit Cost | 2022 Total | 2025 Total
Flex posts (10' spacing) for contraflow lane | Each |  | 14 | 50 | 54.615 | 9800 | 10704.54
Flex posts (10' spacing) for additional use | Each |  | 0 | 50 | 54.615 | 0 | 0
Bicycle-friendly speed humps | Each |  | 0 | 5000 | 5461.5 | 0 | 0
Curb Extensions | Per Intersection |  | 0 | 20000 | 21846 | 0 | 0
Landscaped Chicanes | Each |  | 0 | 7500 | 8192.25 | 0 | 0
Raised Crosswalk | Each |  | 0 | 10000 | 10923 | 0 | 0
Raised Intersection | Each |  | 0 | 50000 | 54615 | 0 | 0
Mini-Roundabout | Per Intersection |  | 0 | 50000 | 54615 | 0 | 0
Bicycle-friendly storm grates | Each |  | 0 | 7500 | 8192.25 | 0 | 0
Construction Subtotal |  |  |  |  | 0 | 39412.5 | 43050.2738
Mobilization | 10% of Construction Costs |  |  | $750,000 per Location (2022) |  | 2022 Total | 2025 Total
Subtotal |  |  |  |  | 0% | 39412.5 | 43050.2738
Contingency | 10% of Construction Costs |  |  | 10% |  | 3941.25 | 4305.0274
Construction Subtotal | [5 empty] | 43353.75 | 47355.3011
Design & Permitting | 25% of Construction Costs |  |  | 25% |  | 10838.4375 | 11838.8253
Preliminary Site Investigation | 10% of Design |  |  | 10% |  | 1083.8438 | 1183.8825
0
Project Costs | [5 empty] | 55276.0312 | 60378.0089

## Shared-Use Paths
Planning Level Cost Estimates for Shared-use Paths
Project Description
Facility Type | Context | Length (feet) | Length (Miles) | Trail 2022 Base Cost per mile | Trail 2025 Base Cost per mile | 2022 Total Cost per mile | 2025 Total Cost per mile
Shared-use Path | Stream Valley | 0 | 0 | 1750000 | 1911525 | 0 | 0
| Steep terrain | 0 | 0 | 2500000 | 2730750 | 0 | 0
| Rolling Terrain | 0 | 0 | 1250000 | 1365375 | 0 | 0
| Level Terrain | 36432 | 6.9 | 1100000 | 1201530 | 7590000 | 8290557
Subtotal |  |  | 6.9 |  |  | 7590000 | 7764570
Pervious Pavement |  | No |  | 0.5
Subtotal | [5 empty] | 7590000 | 8290557
Retaining Walls |  | Length (feet) | Length (Miles) | Retaining Wall 2022 Cost ($100 per square foot) | Retaining Wall 2025 Cost ($100 per square foot) | 2022 Total | 2025 Total
| Wall 1 | 0 | 0 | 100 | 109.23 | 0 | 0
| Wall 2 | 0 | 0 | 0 | 0 | 0 | 0
| Wall 3 | 0 | 0 | 0 | 0 | 0 | 0
Bridges |  | Length (feet) | Length (Miles) | Bridges 2022 Cost (per square foot) | Bridges 2025 Cost (per square foot) | 2022 Total | 2025 Total
| Bridge 1 | 0 | 0 | 400 | 436.92 | 0 | 0
| Bridge 2 | 0 | 0 | 400 | 436.92 | 0 | 0
| Pre-fabricated Bridge 1 | 0 | 0 | 125 | 136.5375 | 0 | 0
| Pre-fabricated Bridge 2 | 0 | 0 | 125 | 136.5375 | 0 | 0
Boardwalk |  | Length (feet) | Length (Miles) | Boardwalk 2022 Cost ($45-$150 per square foot) | Boardwalk 2025 Cost ($45-$150 per square foot) | 2022 Total | 2025 Total
| Boardwalk 1 | 0 | 0 | 45 | 49.1535 | 0 | 0
| Boardwalk 2 (w raillings) | 250 | 0.047348 | 150 | 163.845 | 525000 | 573457.5
|  | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0
Tunnels |  | Length (feet) | Length (Miles) | Tunnel 2022 Cost ($2600 per square foot) | Tunnel 2025 Cost ($2600 per square foot) | 2022 Total | 2025 Total
| Tunnel 1 | 0 | 0 | 2600 | 2839.98 | 0 | 0
| Tunnel 2 | 0 | 0 | 400 | 436.92 | 0 | 0
Lighting |  | Length (feet) | Length (Miles) | Lighting Cost 2022 ($1m per linear mile) | Lighting Cost 2025 ($1m per linear mile) | 2022 Total | 2025 Total
| Section 1 | 500 | 0.094697 | 1000000 | 1092300 | 94696.9697 | 103437.5
| Section 2 | 0 | 0 | 1000000 | 1092300 | 0 | 0
Railroad Protection Services |  | Locations |  | $750,000 per Location (2022) | $819,225 per Location (2052) | 2022 Total | 2025 Total
| Location | 0 |  | 750000 | 819225 | 0 | 0
Construction Subtotal | [5 empty] | 8209696.9697 | 8967452
Mobilization | 10% of Construction Costs |  |  | 10% |  | 820969.697 | 896745.2
Subtotal | [5 empty] | 9030666.6667 | 9864197.2
Contingency | 30% of Construction Costs |  |  | 30% |  | 2709200 | 2959259.16
Construction Subtotal | [5 empty] | 11739866.6667 | 12823456.36
Design & Permitting | 25% of Construction Costs | 0.25 |  | 25% |  | 2934966.6667 | 3205864.09
Preliminary Site Investigation | 10% of Design | 0.15 |  | 10% |  | 293496.6667 | 320586.409
Project Costs | [5 empty] | 14968330 | 16349906.859